## Prework
Requirements | Technician Responses
Is there other EOL infrastructure?
Possible Solution #1
Possible Solution #2
Possible Solution #3
Best Fit Solution:
Why is this the best fit?
Previous similar Sales Scopes
Previous scope #1
Previous scope #2
Other related documents:
Note on A2: Zachary Cramer: if server, firewall, network switch or wireless will be EOL in the next 6 months STOP and return to this to the project coordinator.
Note on A5: Zachary Cramer: Only 2 are required, but feel free to do as many as you want if you have more ideas.
Note on A8: Charlie Dean: Include considerations like cost, scaleability, EOL equipment, etc
Note on A11: Sarah Lentini: At least one previously created ITA scope is required but feel free to add additional scope to the list

## Tasklist
DO NOT SAVE OVER THIS TEMPLATE (Current as of 7/10/2024)
Project Name: | Project Ticket Number: | Sales Scope Prepared by: | 2nd Technical Reviewer Sign-Off | Admin Reviewer Sign-Off | Filled out by ProjCo Time Tech Spent Scoping (hrs.) Not Auto Included in Labor Total | Date of scope creation
Please color code your task list:(Use these to call out roles/location) ITA_office/Remote - Blue, ITA_client onsite - Purple, Vendor Responsibility - Red, Client Responsibility - Yellow, Procurement - Green
Task - Please separate tasks by the day it will occur - hours cannot exceed 8hrs a day including travel i.e. Day 1, Day 2-5, Day 6 | Comments Identifier | Time Est Minimum | Time Est Avg | Time Est Max | TIER | Downtime? | Afterhours?
Day 1 - 8hrs max |  |  | 0 | 0
Travel time bi-directional (remove if unnecessary) |  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
Final/EOD onsite walk through w/ client POC (remove if unnecessary) |  |  | 0 | 0
|  |  | 0 | 0
Day 2 - 8hrs max |  |  | 0 | 0
Travel time bi-directional (remove if unnecessary) |  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
Final/EOD onsite walk through w/ client POC (remove if unnecessary) |  |  | 0 | 0
|  |  | 0 | 0
Day 3 - 8 hrs max |  |  | 0 | 0
Travel time bi-directional (remove if unnecessary) |  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
Final/EOD onsite walk through w/ client POC (remove if unnecessary) |  |  | 0 | 0
|  |  | 0 | 0
Day 4 - 8 hrs max |  |  | 0 | 0
Travel time bi-directional (remove if unnecessary) |  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
Final/EOD onsite walk through w/ client POC (remove if unnecessary) |  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
At completion of project:
Update ITGlue |  |  | 0 | 0
Deprecate old ITGlue entries |  |  | 0 | 0
Notify Project Coordinator if any task was not performed or if the project did not achieve its stated goal
Downtime Estimates
Estimated Downtime Total: |  | 0 | 0 | 0
Recommended After Hours Labor |  | 0 | 0 | 0
| Labor Total | 0 | 0 | 0
| Troubleshooting (25%) | 0 | 0 | 0
| Total (Hours) | 0 | 0 | 0
| Proj Mgmt (20% of labor before "At completion of Project" | 0 | 0 | 0
Labor Quoted:
Sales Notes:
Downtime Explanation(s)
If there will be downtime - what of the clients workflow will be affected?
Please be specific
Parts Needed: *Please add alternative options for all major hardware Please include any: Ethernet cables, velcro/zip ties, or other mounting hardware needed? | Quantity | MFG part number: | URL: | Vendor Total QTY Price: | Hardware Alternative:
0
0
0
0
0
0
0
0
|  |  | Total: | 0
Client Dependencies:
Would this project involve cat-herding ? (Y/N):
Vendor Dependencies:
| Vendor 1: | Vendor 2: | Vendor 3:
Is the clients support contract current:
Does the vendor charge for the action you need help with:
Is there already a ticket open with them? (Add #)
Vendor contact:
Business hours:
Comments:
Note on A2: Please delete checklists that are NOT applicable to the project and complete the checklists that ARE applicable
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technical reviewer dependant on scope requirements - Please check with ProjCo if this is required
Note on A52: Include links to parts needed, part numbers, and quantities.
Note on E52: Sarah Lentini: Pricing is direct from purchasing website and does NOT include: - Shipping cost - Hourly/MSP markups
Note on A62: Dependencies are aspects of this project that rely on an outside vendor or additional coordination. Some examples of this include need for external IP addresses, need for low voltage work, need for a different projcet to be completed first, etc. Technicians are responsible for coordinating any work that includes technical knowledge.

## Hypervisor Checklist
Question: | Answer:
1. Initial communication and pre-scoping: (completed by Project Coordinator)
Do we have contact info for all potentially involved vendors?
Do we know what function(s) the new server is going to provide?
2. Scoping:
a. New Server must meet physical specs to accommodate 5 years of use:
If rack mounted, is the current rack sufficient, does it have enough space, and what type of mounting holes does it have?
Does the current switch have enough open ports to accommodate the new server, and does the speed of the switching equipment meet or exceed the needs of the server?
Is there enough RAM to adequately run all of the functions the server is going to provide?
Have you configured a minimum of RAID10 for HDDs, and RAID1 for SSDs?
Is the disk array fast enough? (Hint: HDDs are very slow and not recommended today unless in RAID10 with 6 disks or more, get SSDs if possible)
Can an additional CPU be added? Is the organization likely to grow enough in 5 years to need another CPU?
Is the server built with the maximum number of drive bays and have you verified that the number of open bays is adequate for the next 5 years of use?
Have you included two network ports at minimum with any additional network cards being Intel?
Have you included dual PSUs?
Have you verified that the existing UPS can handle the power load?
Have you included all necessary cabling?
b. Impact on the rest of the network:
Have you confirmed if ANY ip addresses will change and who will this impact?
c. Time estimating:
Have you included time needed for completing the scoping document?
Have you included time for unboxing and physically setting up any equipment?
For any necessary data transfer time have you taken into account quantity of files, total size of data, and transmission speeds? | (Robocopy can test file and folder copy time, add this to the how to doc)
If we are doing a virtual to virtual migration have you confirmed with the related vendor(s) that a migration is supported?
Does a software or OS upgrade need to occur before a migration?
Have you included time needed for user testing?
d. Vendors:
Have all vendor softwares been identified?
Have all software vendors been contacted and their involvement identified in the tasklist?
4. Testing:
Have you identified all access methods to the server, and accounted for this in implementation and testing?
If we are virtualizing a physical server, have you test run the resulting virtual machine using a client contact?
5. Implementation:
Project Coordinator: Create a step-by-step task breakdown for day of implementation
Has the client tested and verified functionality?
Have all users been given instructions for workflow changes?
6. Post Project:
Is there a tech scheduled for an on-site the next business day with a specific list of items to verify with users?
Have you had a project info meeting or emailed with Service Manager to explain impacts of the project?
Have you updated all relevant ITGlue documentation and processes and included links to them here?
Project Coordinator: Reach out to client with the post project process

## VM Checklist
DONE | Question: | Answer:
1. Initial communication and pre-scoping: (completed by Project Coordinator)
Do we know what function(s) each new VM is going to provide?
2. Scoping:
a. New VM(s) must meet or exceed the requirements for its function(s):
Have you verified that the new VM being created has sufficient resources for its function?
Have you verified that the VM host can handle the hardware requirements at 100% utilization for the new VM?
Have you verified that the disk speed and capacity are acceptable with the application requirements that the VM will be hosting?
Have you verified the VM host has the network capacity to handle the new VM requirements?
Have you verified the new VM has the correct install of Windows Server and that the appropriate licensing has been added to the sales scope?
Have you verified that the backup storage will be large enough to successfully back up the VM for the retention period set for that client?
b. Impact on the rest of the network:
Have you confirmed if ANY ip addresses will change and who will this impact?
Will any network settings need to be updated on workstations?
c. Time estimating:
Have you included time needed for completing the scoping document?
For any necessary data transfer time have you taken into account quantity of files, total size of data, and transmission speeds?
If we are doing a physical to VM migration have you confirmed with the related vendor(s) that a migration is supported?
Does a software or OS upgrade need to occur before a migration?
Have you included time needed for user testing in total time estimate?
d. Vendors:
Have all vendor softwares been identified?
Have you verified if we need to work with any vendors as part of the VM setup that we have communicated with them and have accurate time estimates of work needed by them for setup or have accurately validated the time it will take for us to set up their application?
4. Testing:
Have you identified all access methods to the server, and accounted for this in implementation and testing?
5. Implementation:
Project Coordinator: Create a step-by-step task breakdown for day of implementation
Has the client tested and verified functionality?
Have all users been given instructions for workflow changes?
6. Post Project:
Is there a tech scheduled for an on-site the next business day with a specific list of items to verify with users?
Have you had a project info meeting or emailed with Service Manager to explain impacts of the project?
Have you updated all relevant ITGlue documentation and processes and included links to them here?
Project Coordinator: Reach out to client with the post project process

## Firewall Checklist
DONE | Question: | Answer:
1. Initial communication and pre-scoping: (completed by Project Coordinator)
Do we have contact info for all potentially involved vendors?
Are there any Country Blocking exclusions needed? If so, what are they?
Is the client using a static IP and do we have that information on file?
Will any users need VPN set up and do we have the list of users on file?
2. Scoping:
a. New firewall must meet the requirements in the firewall scoping guide:
Did you verify that the new firewall is fast enough to handle the ISP speed, plus growth of ISP speed?
Did you verify if any NATting is required and account for the time involved in creating and testing the rules?
Did you verify if there are any additional firewall rules required and account for the time involved in creating and testing the rules?
Did you verify if you are setting up VPN and account for the time involved in setup, documentation, testing, and instruction for users?
Did you verify if the modem needs to be put into bridge mode?
Did you verify if the client's needs require or could benefit from a static IP?
Has a site survey been done to confirm they have enough ports, bandwidth between network devices, and space for the new firewall to be installed?
Did you verify if a rack mount kit is needed for firewall?
Did you confirm that you're scoping the correct color of any ethernet cables needed, according to our cable color coding guide?
Did you verify that the correct fiber module has been selected for the fiber cable, speed, and wavelength?
Did you verify that the firewall model selected is the appropriate model per the scoping guide?
Did you verify that correct support plan has been selected per the scoping guide?
Did you verify that any devices connecting to the firewall have compatible firmware or hardware? (Fortiswitch, Fortiap)
Have you included all necessary cabling?
b. Impact on the rest of the network:
Have you confirmed if ANY ip addresses will change and who will this impact?
Will any network settings need to be updated on workstations?
c. Time estimating:
Have you included time needed for completing the scoping document?
Have you included time for unboxing and physically setting up any equipment?
Do any firmware upgrades need to occur before deployment? (Such as existing switches or AP's)
Have you included time needed for implementation user testing in total time estimate?
d. Vendors:
3. Hardware Checklist:
Project Coordinator: Create a list of any hardware being deployed
4. Testing:
Have you test run any new VPN or other workflow changes using a client contact?
5. Implementation:
Project Coordinator: Create a step-by-step task breakdown for day of implementation
Has the client contact tested and verified functionality?
Have all users been given instructions for workflow changes?
6. Post Project:
Have you had a project info meeting or emailed with Service Manager to explain impacts of the project?
Have you updated all relevant ITGlue documentation and processes and included links to them here?
Project Coordinator: Reach out to client with the post project process

## Switching Checklist
DONE | Question: | Answer:
1. Initial communication and pre-scoping: (completed by Project Coordinator)
Do we have contact info for all potentially involved vendors?
| 2. Scoping: | *Link - How to thing
a. New [device] must meet physical specs to accommodate 5+ years of use:
Verify that number of ports on switches meets customer needs
Verify the network rack has enough physical space for the new switches
Verify that 10GB is used between firewall and all downstream switches where possible
Verify that switching being connected together have at minimum 2 links between each switch if configured in a stack
Verify that if fiber is being used that the modules selected will work in the customers environment with existing fiber runs if applicable.
Verify that all new coper patch cables are included in the quote to run from the patch panel to the new switching equipment
Verify that all new coper patch cables added to the quote follow our color guide, are the correct length, and are cat6 or higher rating
Verify that all new fiber cables are included in the quote to run from the fiber bulkhead and between all switching equipment
Verify that all new fiber cable is OM4 for multi mode and is OM2 for single mode cable and verify the cable is the correct length for the run
Verify that if using DAC (Direct Attach Copper Cables), Twinax, or stacking cables that the cable lengths are correct and have been verified
b. Impact on the rest of the network:
Have you confirmed if ANY ip addresses will change and who will this impact?
c. Time estimating:
Have you included time to unbox, update firmware, and register devices before deployment?
3. Hardware Checklist:
Project Coordinator: Create a list of any hardware being deployed
4. Testing:
5. Implementation:
6. Post Project:
Have you had a project info meeting or emailed with Service Manager to explain impacts of the project?
Have you updated all relevant ITGlue documentation and processes and included links to them here?
Project Coordinator: Reach out to client with the post project process

## Wireless Checklist
DONE | Question: | Answer:
1. Initial communication and pre-scoping: (completed by Project Coordinator)
Do we have contact info for all potentially involved vendors?
Do we have floor plans for the areas being scoped?
Who is the project approver and on-site contact, and how do we get ahold of them?
2. Scoping:
a. New [device] must meet physical specs to accommodate [5+] years of use:
Confirm the number of wifi clients matches the capacity of the proposed solution
Confirm the wifi data transfer load matches the capacity of the proposed solution (ex: are clients performing backups or large data transfers over WiFi simultaneously as VOIP calls?)
Have you created a heatmap estimate via software to confirm coverage?
Verify where the client wants wireless coverage and validate we have accounted for it with the number of WAPs scoped
Verify that enough WAPs have been scoped to compensate for density of wireless devices on the network
Confirm the correct licensing and support contracts are included with the hardware
Do we have the correct hardware to mount to the surface? EX: Concrete anchors, wood screws, etc?
Can we reach the ceiling or location where the AP's will be placed? Do we need a lift?
Verify that the APs will have PoE power through a switch or injector
Verify that we have low voltage contractor to run cable or mount the AP's if needed.
Verify that the WAP model selected is on our list of supported wireless devices
Do you have the correct cables to patch in the WiFi AP's?
b. Impact on the rest of the network:
Has the wifi password changed?
Do devices need to be configured on a MAC address allow list?
Are there any 802.1x authentication protocols in place?
c. Time estimating:
Did you include time for unboxing, updating firmware, and registering the AP's
Did you include time for physically mounting the AP's?
d. Vendors:
3. Hardware Checklist:
Project Coordinator: Create a list of any hardware being deployed
4. Testing:
5. Implementation:
6. Post Project:
Have you had a project info meeting or emailed with Service Manager to explain impacts of the project?
Have you updated all relevant ITGlue documentation and processes and included links to them here?
Project Coordinator: Reach out to client with the post project process

## Battery backup Checklist
DONE | Question: | Answer:
1. Initial communication and pre-scoping: (completed by Project Coordinator)
Do we have contact info for all potentially involved vendors?
Who is the project approver and on-site contact, and how do we get ahold of them?
2. Scoping:
a. New [device] must meet physical specs to accommodate [#] years of use:
Verify load by watts and time needed for UPS to keep devices power for is correct for the UPS. Servers require a minimum of 30 minutes, network equipment requires minimum of 15 minutes
Verify that if the unit is rack mounted that a rack mount kit is included in the scope for the correct rack type, 2 post or 4 post
Verify the UPS includes a network management card (environmental monitoring required for servers)
If the client has a server, verify the UPS has a temperature sensor
Verify that you have a picture of where the UPS will be plugged into and validate that the input plug on the UPS is compatible with the customer's power outlet
Verify the amperage of that outlet and then validate that the UPS does not exceed the amperage capacity
Verify voltage for that outlet is compatible with the UPS
Verify that the UPS output outlets are the correct type for the devices that will be plugged into them
Verify that this UPS will be suitable for the customers equipment for 5 years and has room for expansion if the client will be adding devices in the future
Have you included all necessary cabling?
b. Impact on the rest of the network:
c. Time estimating:
Have you included time to unbox and test the UPS prior to deployment?
Have you included time to configure the network management card
Have you included time to install and configure network shutdown software automations and SMTP notifications?
d. Vendors:
3. Hardware Checklist:
Project Coordinator: Create a list of any hardware being deployed
5. Implementation:
6. Post Project:
Have you had a project info meeting or emailed with Service Manager to explain impacts of the project?
Have you updated all relevant ITGlue documentation and processes and included links to them here?
Project Coordinator: Reach out to client with the post project process

## Phones Checklist
DONE | Question: | Answer:
1. Initial communication and pre-scoping: (completed by Project Coordinator)
Do we have the phone planning worksheet filled out by the client?
Do we have contact info for all potentially involved vendors?
Who is the project approver and on-site contact, and how do we get ahold of them?
2. Scoping:
| 3. Hardware Checklist: |  | Hardware checklist
Project Coordinator: Create a list of any hardware being deployed
4. Testing:
5. Implementation:
6. Post Project:
Have you had a project info meeting or emailed with Service Manager to explain impacts of the project?
Have you updated all relevant ITGlue documentation and processes and included links to them here?
Project Coordinator: Reach out to client with the post project process

## Network Rack Checklist
DONE | Question: | Answer:
1. Initial communication and pre-scoping: (completed by Project Coordinator)
Do we have contact info for all potentially involved vendors?
Do we have photos of the network rack area?
Who is the project approver and on-site contact, and how do we get ahold of them?
2. Scoping:
a. New [device] must meet physical specs to accommodate [5+] years of use:
Enough Rack Units to accommodate all current equipment
Has at least 4U of extra space for maneuvering
Enough space for future expansion to meet the clients needs
Deep enough to fit the network equipment you want to mount (PoE switches can be up to 20" deep for example)
Deep enough to fit the server equipment you want to mount (servers are around 32" deep but can be larger)
Uses cage nuts (suare holes, not threaded screw holes)
*Cabling*
Make sure the current patch panel has enough slack to move and mount in the new rack. If not, include a passthrough patch panel and associated cabling in the scope
c. Time estimating:
Did you include time for unboxing, assembling, and mounting the rack?
Did you include time for mounting the equipment and cable management?
d. Vendors:
3. Hardware Checklist:
Project Coordinator: Create a list of any hardware being deployed
4. Testing:
5. Implementation:
6. Post Project:
Have you had a project info meeting or emailed with Service Manager to explain impacts of the project?
Have you updated all relevant ITGlue documentation and processes and included links to them here?
Project Coordinator: Reach out to client with the post project process

## ChangeLog
2020-01-14 | Rainbow suggested to use Hours instead of Mins. I added using .5 or 1 as units only. Helps when converting to minutes.
2020-05-07 | Updated formatting, spelling, included conditional formatting, inserted notes, added room for scope ticket as well as project ticket - charlie@itassurance.com
10/21/2020 Removed BMS tab that we don't use, added PreScoping tab. -Charlie@itassurance.com
10/23/2020 Added standardizations to checklists, included estimated downtime formula - charlie@itassurance.com
2023-10-01 | Added Sales Notes charlie@itassurance.com
2/20/2024 | Updated scope section in checklists kevin@itassurance.com
2/29/2024 | Removed Client Complexity Position and Client Complexity Position from the Prework tab,
2024-07-11 | Included Scope creation date in tasklist tab - catalinah@itassurance.com